## Sheet1
| User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
THE BASIC REQUESTS CONT. (POST , PUT , DELETE, GET)
1 | TIQ admins should be able to delete content on the TIQ subdomain | 1 | Mohamed | Youssef | Kamal
1.1 | TIQ admins should be able to update content on the TIQ subdomain | 2 | Mohamed | Youssef | Kamal
2 | TIQ admin should be able to update users(the alumni's and mates') information | 2 | Nada | Kamal | Nadin
2.1 | TIQ admin should be able to delete users(the alumni's and mates') with their information | 1 | Nada | Kamal | Nadin
3 | TIQ admin should be able to update users(Disciples and parents) information | 2 | Nadin | Bassant | Nada
3.1 | TIQ admin should be able to delete users(Disciples and parents) with their information | 1 | Nadin | Bassant | Nada
4 | TIQ admins should be to update debates | 2 | Menna | Nada | Bassant
4.1 | TIQ admins should be able to delete debates | 1 | Menna | Nada | Bassant
5 | Users should be able to update their own profiles | 2 | Kamal | Youssef | Nada
6 | TIQ admins should be able to update articles | 2 | Youssef | Kamal | Bassant
6.1 | TIQ admins should be able to delete articles | 1 | Youssef | Kamal | Bassant
7 | TIQ admins should be able to delete the Debate lives | 1 | Bassant | Nada | Menna
OTHER USER STORIES TO BE IMPLEMENTED IN THE FRONT END
8 | As a Hub admin I should be able to answer the users (logged in & not-logged-in) questions in order to provide solutions for any thing told by the users and to have direct interaction with people surfing the website on the FAQ section in the HUB page | 1 | Nouran | Seif | Nada
8.1 | As a Hub admin I should be notified by the questions of the users in order to provide fast client services on the FAQ section in the HUB page | 1 | Seif | Nouran | Kamal
8.2 | As a user I should be able to ask questions on the Hub in order to know or understand something that is not mentioned on the platform or even if I need a solution of a certain problem related to platform on the FAQ section in the HUB page | 1 | Nouran | Seif | Nada
8.4 | As a user I should be notified by the answers of my questions in order to solve or know the thing I have asked for faster on the FAQ section in the HUB page | 1 | Seif | Nouran | Kamal
9 | Logged in users should have their own profiles within Hub including their information | 2 | Kamal | Youssef | Bassant
9.1 | Hub main Homepage should include all the participating clubs along with with breif description on each one. | 1 | Kamal | Nada | Youssef
10 | Users should be able to sign up on the HUB using the the registration form | 1 | Menna | Nadin | Nada
10.1 | Users should be able to log in and out from their accounts | 2 | Menna | Bassant | Nada
11 | As a user I want to search debates by date on TIQ page in order to facilitate going through the whole debates on the website to find the wanted one using the search bar in TIQ homepage | 1 | Menna | Nouran | Bassant
11.1 | As a user I want to search debates by category on TIQ page in order to facilitate finding the wanted debate and also to provide flexibility to the users to find debates according to their interests through the search bar on the navigation bar of TIQ page | 1 | Menna | Nouran | Bassant
11.2 | Users should be able to search for other users by the name (either the first name or the last name) using the search bar on TIQ homepage | 1 | Nada | Seif | Mohamed
11.3 | Users should be able to search for other users by the type through the search bar on the navigation bar of TIQ page | 1 | Nada | Seif | Mohamed
11.4 | Users should be able to search for articles by any word in the title through the search bar on the navigation bar of TIQ page | 1 | Youssef | Nada | Kamal
11.5 | Users should be able to search for motions of the chatbar by any word the title through the search bar on the navigation bar of TIQ page | 1 | Bassant | Nouran | Nadin
12 | A user should be able to comment on any article on the Blog page in order to be able to interact and give opinions on certain topics | 1 | Youssef | Bassant | Kamal
12.1 | Users should be able to redirect to the author's profile on the About us page form the Article page | 2 | Youssef | Bassant | Kamal
13 | Scores of each house should always be on update (dynamically) in order to show the progress of each house and view which house is leading and it will be viewed on the TIQ homepage | 2 | Nada | Kamal | Menna
13.1 | Latest updates of TIQ should be view on the main Homepage of TIQ in order to make it easier for users to catch up with any of the events created | 1 | Nada | Kamal | Menna
14 | Hierarchy of TIQ (The TIQ tree) should be view on the About us page for the users to understand more about the enviroment of TIQ | 2 | Nadin | Nouran | Mohamed
14.1 | Mates and Alumni' names and description will be all viewed on the About us in TIQ page | 1 | Nadin | Nouran | Mohamed
15 | The social media links related to TIQ will be view on the contact us page on TIQ page | 1 | Mohamed | Bassant | Nada
16 | Number of responses of certain Debate live should be included along with the for and against repsones on the Debate Live section. | 1 | Bassant | Nada | Menna
16.1 | Users should be able respond to debate live so that they can interact more on the website and have a full experience on the Debate Live section on TIQ page | 1 | Bassant | Nada | Menna
16.2 | Users should be notifed (the notification bar ) that they are mention in a certain motion in the Debate Live | 1 | Bassant | Nada | Menna